## Sheet1
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic | < Impact
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
^ Likelihood
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level | Recognition Date
RSI | I could develop RSI | Ensure to stretch regularly | Ensure I don’t develop RSI which Could impact my future | Very Unlikely | Minor | 1 | 2022-04-29
Coming across new, Unfamiliar technologies | Coming across technologies or techniques that I don’t understand could cause delays in my project. | Keep up to date with new coding techniques that could benefit me on my Project. | Try to keep up to date and informed on the techniques and technologies that I will be using throughout my project and if uncertain, research solutions to my problems and learn Effective solutions. | Moderate | Minor | 3 | 2022-04-29
Not completing all requirements as expected | I could misinterpret a requirement which would cause my project to not work as expected. | Ensure to be thorough when reading through the requirements for my project. | Be thorough and specific in my tasks And ensure that I have the correct understanding of each requirement with my trainer before starting my code. | Unlikely | Minor | 2 | 2022-04-29
Becoming fatigued | Becoming fatigues while working could cause my productivity levels to drop resulting in not completing my project before the deadline. | Ensure to take steps to minimise the risk of becoming fatigued | Use ‘eye saver’ mode on my monitor to reduce strain on my eyes. Make sure to sleep well and eat healthily to make sure I’m feeling energised before and throughout the day Make sure to take breaks throughout the day and get fresh air to relax my Mind. | Moderate | Minor | 3 | 2022-04-29
Running out of time to Complete my project | Running out of time could cause me to have to submit my project when it is incomplete. | Ensure to manage my time effectively and create achievable goals to complete my work before the deadline. | Create time goals for my tasks on my Kanban board to ensure that I stay on track and don’t waste too much time on one task. | Moderate | Major | 4 | 2022-04-29
Computer Malfunction | My computer not working as expected could cause me to not be able to continue working on my Project. | Ensure to check my computer health and dust build up regularly. | Monitor computer health regularly and ensure the area around my computer is clean and dust free to reduce the risk of issues such as overheating. | Very Unlikely | Catastrophic | 6 | 2022-04-29
Loss of internet Connection | Loss of internet would prevent me from pushing and pulling from GitHub preventing me from backing my work up, and I would also not be able to contact anyone Through Teams. | Ensure I have a reliable ISP and have data available on my phone as a backup to contact my trainer through teams if necessary. | Regularly push and pull from GitHub To ensure that my work is up to date both locally and in my online Repository. | Unlikely | Hazardous | 5 | 2022-04-29
Power cut | A power cut could cause me to lose work from my project. | Ensure to save my work at regular intervals to reduce the risk of work loss | Regularly save my work and push to GitHub to ensure that if a power cut does occur, I won’t loose a large Amount of work | Unlikely | Hazardous | 5 | 2022-04-29
Losing My Work | Loss of work will affect the entirety of my project and cause me to have To restart my project. | Ensure to save regularly and upload my work to my repository at every step of the process. | Regularly push my work to GitHub and keep my work saved in multiple secure locations to decrease the Likelihood of loosing all of my work. | Unlikely | Catastrophic | 7 | 2022-04-29
Getting aches | Getting aches can result in reduces productivity making my workflow less efficient | Ensure to take regular breaks, stretch and keep a good posture while working on the computer | Reagularly stretch and maintain a good posture while working | Moderate | Minor | 3 | 2022-05-06
Getting Distracted | Getting distracted can reduce productivity and cause you to lose your train of thought | Ensure to keep my phone away from my workspace and wear headphones to reduce the chances of being distracted by occurrances in my surroundings | Create a work focus mode in my phone that only allows important notifications to come through when in work hours. Also create a seperate desktop on my pc to allow a disconnect between work and leisure, to ensure I'm not distracted and that I can take healthy breaks from work out of hours. | Likely | Minor | 4 | 2022-05-06